###### Schedule and Process of New Program Development / Program Modification

###### Academic Year 2021 and implemented in Academic Year 2022

###### (June 1, 2021 – May 31, 2022)

- Time- Frame

- (1)  New Program and (2) Program Modification are required to be completed within the academic year 2021 in accordance with Program Standard Criteria (at least every five years) and expected to be implemented in the academic year 2021 must be proposed to the University Council for approval in its meeting in September 2021 or November 2021 at the latest. (TQF2 required).

- Program Modification with minor changes can be proposed to the University Council for approval in its meeting on September 2021, or November 2021, or February 2022, or May 2022 (SMO 08 required).

| No. | Process | Schedule Academic Year 2021 |
| --- | --- | --- |
|  |  | Round 1 | Round 2 | Round 3 | Round 4 |
| 1. | Dean submits the draft of new program or program modification to Office of the Vice President for Academic Affairs to verify the compliance of program format and regulations stipulates by the OHEC. | G1:May 14, 2021 G2:May 28, 2021 G3:June 11, 2021 | G4:July 30, 2021 G5:August 13, 2021 | Within October 15, 2021 | Within January 14, 2022 |
| 2. | Chairperson/Program Director changes/corrects the draft according to the recommendations of the Office of the Vice President for Academic Affairs. | Within June 25, 2021 | Within August 27, 2021 | Within November 12, 2021 | Within February 12, 2022 |
| 3. | Chairperson/Program Director meets the Program Development Committee to receive their comments and revise the draft accordingly. | Within July 9, 2021 | Within September 10, 2021 | Within November 26, 2021 | Within March 12, 2022 |
| 4. | Dean/Program Director fills in the information of the new program/program modification in the CHE Curriculum Online (CHECO) | July 16, 2021 | September 17, 2021 | December 15, 2021 | March 30, 2022 |
| 5. | Dean/Program Director proposes the final draft of : New program to the President and the Vice President for Academic Affairs for their considerations on the aptness of proposed draft. Program modification to the Vice President for Academic Affairs for his consideration on the aptness of proposed draft | July 16, 2021 | September 17, 2021 | December 15, 2021 | March 30, 2022 |
| 6. | Chairperson/Program Director meets University Academic Committee to receive their comments/ endorsement for new program/ program modification. | August 2021 G1:5 Programs G2:5 Programs G3:5 Programs | October 2021 G4:5 Programs G5:5 Programs | January 2022 | April 2022 |
| 7. | Dean/Program Director updates the information in the CHE Curriculum Online according to revision made in the TQF2 hard copy. | August 27, 2021 | October 29, 2021 | February 11, 2022 | May 14, 2022 |
| 8. | Chairperson/Program Director meets University Council for its final approval for the implementation of new program/program modification. | September 2021 | November 2021 | February 2022 | May 2022 |
| 9. | Office of the Vice President for Academic Affairs submits the approved program to OHEC for its acknowledgement through the OHEC online system (CHE Curriculum Online). | Within 7 days after receiving the University Council Approval |
| 10. | Office of the Vice President for Academic Affairs follows up the OHEC’s acknowledgement process. | Within 15 days after submitting the approved program |
| 11. | Office of the Vice President for Academic Affairs will inform the chairperson/program director to revise the program according to the OHEC’s comments, if any. | Within 15 days after receiving recommendation of OHEC |
| 12. | Program Implementation | 1/2022 (June 2022) New Program (TQF2)/ Modified Program (SMO08) | 2/2022 (November 2022) Modified Program (SMO 08) |